Sprint 3 Plan

Team Name: SlugSync

Scrum Master: Ridhin

Product Owner: Jayna

Sprint Start Date: 7/13

Completion Date: 7/19

Revision #: 1

Goal: Expand SlugSync beyond manual event management by adding Instagram-sourced event ingestion, AI-generated event recommendations based on user preferences, friend connections with shared free/busy availability, and a consistent design system across the Dashboard, Calendar, and Profile pages.

User Story 3.1 ("As a user I want to be able to click on an event and see its details and full description so I can decide if it's something I want to attend") — 3 pts

- Task 1: Build a read-only event detail modal showing title, full description, date, time, location, and source (2.5 hrs)

- Task 2: Wire up the Dashboard event cards so clicking one opens the detail view (1.5 hrs)

- Task 3: Ensure the description field is stored and rendered correctly from the events table (1 hr)

- Task 4: Style the detail view to match the app's design system (1.5 hrs)

- Task 5: Fix any UI or display errors (0.75 hrs)

User Story 3.2("As a user I want to log in or sign up as the first thing I see, since the app requires an account, so I can securely access my calendar and data") — 5 pts

- Task 1: Gate the app so unauthenticated users are routed to login/signup before anything else loads (2.5 hrs)

- Task 2: Build/refine the signup and login flows with validation and error handling (3 hrs)

- Task 3: Fix session handling so login persists across refreshes and the "Auth session missing" issue is resolved (3 hrs)

- Task 4: Add logout, and redirect authenticated users to the dashboard / unauthenticated ones to login (2 hrs)

- Task 5: Style the login/signup page to match the design system and fix any auth/routing errors (2 hrs)

User Story 3.3 ("As a user I want to be able to add a website of my choice for events to be parsed from so I can keep updated with events from places I like") — 8 pts

- Task 1: Create a sources table in Supabase with RLS policies so users only access their own saved sites (1.5 hrs)

- Task 2: Build the UI for adding, viewing, and removing saved website URLs (3.5 hrs)

- Task 3: Write an Edge Function that fetches the content of a given URL (2.5 hrs)

- Task 4: Extend the Edge Function to parse events from the page text using the AI (2.5 hrs)

- Task 5: Add URL validation and handle failure cases — blocked fetches, empty pages, no events fou I nd (4 hrs)

- Task 6: Show parsed events to the user for confirmation before saving (2.5 hrs)

- Task 7: Save confirmed events to the events table (1.5 hrs)

- Task 8: Fix any UI or integration errors (1 hr)

User Story 3.4("As a user I want a daily digest of my upcoming schedule and suggested events catered to my interests, so I can start my day informed") — 8 pts

- Task 1: Build a digest section on the dashboard and query the user's upcoming events from Supabase (3.5 hrs)

- Task 2: Write an Edge Function that generates a natural-language schedule summary from the user's events via AI (3 hrs)

- Task 3: Pull the user's interests from their profile and use them to generate AI-suggested community events (4 hrs)

- Task 4: Handle empty and failure states — no events, no interests, AI error (2 hrs)

- Task 5: Style the digest to match the design system and fix any integration errors (2.5 hrs)

- User Story 3.5 ("As a user I want to add friends and view their schedules so that we can coordinate hangouts") — 5 pts

  - Task 1: Build user search and add-friend functionality (2 hrs)

  - Task 2: Build the friends-list UI (1 hrs)

  - Task 3: Build shared free/busy availability view for friends (2 hrs)

  - Task 4: Add privacy controls and empty-state handling (1 hrs)

  - Task 5: Test the friend-add and shared-schedule flow (1 hrs)

User Story 3.6("As a user I want a shared group calendar with my friends, so we can see each other's events and plan things together") — 8 pts

- Task 1: Create groups and group_members tables in Supabase with RLS policies (2.5 hrs)

- Task 2: Build UI to create a group and add friends to it (3 hrs)

- Task 3: Add a group path for events and build the group calendar view that merges members' shared events (4 hrs)

- Task 4: Handle permissions and let users switch between personal and group calendars (3 hrs)

- Task 5: Style the group calendar and management UI, and fix any errors (2.5 hrs)

- User Story 3.7 ("As a user I want SlugSync to have a clear, consistent, and modern interface so that I can easily discover events, manage my calendar, and navigate the application") — 5 pts

  - Task 1: Build the design system components — typography, spacing, buttons, cards, forms, navigation, event tags (2.5 hrs)

  - Task 2: Apply the new design to the Dashboard (2.5 hrs)

  - Task 3: Apply the new design to the Calendar without breaking existing functionality (2.5 hrs)

  - Task 4: Apply the new design to the Profile page, keeping Supabase behavior intact (1.5 hrs)

  - Task 5: Build a rough Friends page using the same design system (1 hrs)

  - Task 6: fix any UI-related errors (0.75 hrs)

Sprint 3 total estimated hours: 86.5 hrs

Team Roles:

Jayna: Product Owner/Developer

Emiliano: Developer

Ridhin: Scrum Master/Developer

Richie: Developer

Kevin: Developer

Initial Task Assignment

Remaining Tasks:

Jayna: 3.4,

Emiliano: US 3.1, 3.5

Ridhin: US 3.2, 3.7

Richie: 3.6

Kevin: 3.3

Initial burnup chart: https://github.com/users/Richie59943/projects/4/insights?period=custom&start_date=2026-07-12&end_date=2026-07-19

Initial scrum board: https://github.com/users/Richie59943/projects/4

Scrum times:

- Tuesday, after TA meeting

- Thursday, after TA meeting

- Friday 4pm

## Sprint 3 Definition of Done

A Sprint 3 user story was considered complete when:

- All acceptance criteria for the user story were met.

- The feature worked correctly with the existing SlugSync application.

- The feature was connected to Supabase when database storage or authentication was required.

- The user interface followed the SlugSync design system and worked in both light and dark mode.

- Input validation, loading states, empty states, and basic error handling were included where needed.

- New code did not break existing dashboard, calendar, profile, authentication, or event functionality.

- Relevant unit, integration, or regression tests were added or updated.

- All automated tests passed.

- The production build completed successfully using npm run build.

- The code was reviewed, merged into the team’s final branch, and the related task was closed.

- Any unfinished functionality, edge cases, design shortcuts, or known bugs were documented in the Test Report or Release Summary.

- The feature was demonstrated and accepted by the team based on the user story requirements.