Team Name: SlugSync

Completion Date: 7/5/26 11:59PM

Revision #: 1

Revision Date: 7/2/26

Goal: Establish the core foundation of the app by delivering a functional dashboard, calendar view, account profile, and event management system that users can interact with.

- User Story 1.1 ("As a user I want to see a dashboard so I can decide what events I want to attend") — 3 pts

  - Task 1: Design dashboard layout and component structure in React (1 hrs)

  - Task 2: Create Navigation for Filter Components (1 hr)

  - Task 3: Build dashboard UI components with Tailwind CSS (1.5 hrs)

  - Task 4: Connect dashboard to Supabase to fetch and display events (1 hrs)

Total for User Story 1.1: 3.5 hrs

- User Story 1.2 ("As a user I want to see my calendar so I can view my schedule") — 5 pts

  - Task 1: Research and set up Leaflet/calendar library integration (1.5 hrs)

  - Task 2: Build calendar view component in React (2 hrs)

  - Task 3: Connect calendar to Supabase to pull user schedule data (2 hrs)

  - Task 4: Style calendar with Tailwind CSS (1 hrs)

Total for User Story 1.2: 6.5 hrs

- User Story 1.3 ("As a user I want to have an account profile so I can see my information such as clubs/classes I'm in") — 4 pts

  - Task 1: Set up Supabase auth and user table schema (2 hrs)

  - Task 2: Build account profile page UI in React with Tailwind CSS (2.5 hrs)

  - Task 3: Connect profile page to Supabase to display user info (2 hrs)

Total for User Story 1.3: 6.5 hrs

- User Story 1.4 ("As a user I want to be able to add/delete/edit events to my calendar so I can start building my schedule") — 5 pts

  - Task 1: Design event form component (add/edit) in React (1 hrs)

  - Task 2: Implement add event functionality with Supabase insert (2 hrs)

  - Task 3: Implement edit event functionality with Supabase update (2.5 hrs)

  - Task 4: Implement delete event functionality with Supabase delete (2 hrs)

  - Task 5: Wire event changes to refresh calendar view (1.5 hrs)

Total for User Story 1.4: 9 hrs

Team Roles:

Jayna: (Product Owner/Developer)

Emiliano: (Scrum Master/Developer)

Ridhin: Developer

Richie: Developer

Kevin: Developer

Initial Task Assignment

Jayna: 1.2, task 1, 2, 4

Emiliano: 1.1, task 1, 2

Ridhin: [ 1.3 task 1,2,3x,]

Richie: 1.4, task 1,2,3,4,5

Kevin: 1.1 task 3,4 & 1.2 task 3

∙ Initial burnup chart: https://github.com/users/Richie59943/projects/4/insights/2

∙ Initial scrum board: https://github.com/users/Richie59943/projects/4/views/1

∙ Scrum times:

- Tuesday, after TA meeting

- Thursday, after TA meeting

- Friday 4pm